## 9-2-13
Date: | 2013-07-02 |  |  | Total time: | 6
Tasks | [5 empty] | Reading |  |  |  | Meetings
Task | Due date | Date Complete | % complete | Time spent (hours) | Notes | Author | Title | Chapter Titles | Time Spent | Date | Time
Set up GitHub | 2013-07-02 | 2013-08-30 | 100% | 2 | Handed off to Alex with assignment of responsibility | Github.com | Github Tutorial | Set up Git, Create a repository, Creating and deleting branches within your repository | 0.5 | 2013-08-30 | 1
Android Tutorial | 2013-07-02 |  | 0% | 0 | Ran out of time this weekend. Will complete in the next few days
Project Plan | 2013-07-02 | 2013-07-02 | 40% | 2.5 | Will be finished after the 8pm deadline

## 9-9-13
Date: | 2013-07-09 |  |  | Total time:
Tasks | [5 empty] | Reading |  |  |  | Meetings
Task | Due date | Date Complete | % complete | Time spent (hours) | Notes | Author | Title | Chapter Titles | Time Spent | Date | Time
Android Tutorial | 2013-09-04 | 2013-09-08 | 100% | 0.75 |  | Github.com | Github Tutorial | Set up Git, Create a repository, Creating and deleting branches within your repository | 0.5 | 2013-07-06 | 0.5
Build Robot | 2013-09-06 | 2013-09-03 | 100% | 4
Set up Vex Dev Environment | 2013-09-04 | 2013-09-07 | 100% | 9
Find motor spec Sheets | 2013-09-08 | 2013-09-07 | 100% | 0.5 | Start 2:30
Code individual Motor motion | 2013-09-08 | 2013-09-07 | 100% | 0.25 | Start 3:00
Test individual Motor Motion | 2013-09-08 | 2013-09-07 | 100% | 0.25
Replace 3-wire motors with 2-wire | 2013-09-06 | 2013-09-07 | 100% | 0.75 | Start 3:30
Code Forward/Backward/Left/Right | 2013-09-08 | 2013-09-07 | 100% | 0.75
Test Forward/Backward/Left/Right | 2013-09-08 | 2013-09-07 | 100% | 0.25
Read documentation on Vex Controller Communication | 2013-09-08 |  | 5% | 0.5

## 9-16-13
Date: | 2013-07-09 |  |  | Total time:
Tasks | [5 empty] | Reading |  |  |  | Meetings
Task | Due date | Date Complete | % complete | Time spent (hours) | Notes | Author | Title | Chapter Titles | Time Spent | Date | Time
Write and test sending ssh movement commands from pc | 2013-09-18 |  | 10% | 3 |  | Android.com | N/A | Building a Dynamic UI with Fragments, Creating a Fragment | 0.5 | 2013-09-13 | 0.5
Investigate ssh on android | 2013-09-11 |  | 15% | 3
Write android end of vex-android communcation | 2013-09-14 |  | 10% | 6.5

## 9-23-13
Date: | 2013-09-23 |  |  | Total time: | 11
Tasks | [5 empty] | Reading |  |  |  | Meetings
Task | Due date | Date Complete | % complete | Time spent (hours) | Notes | Author | Title | Chapter Titles | Time Spent | Date | Time
Android to Vex Comm | 2013-09-18 |  | 90% | 9 |  | LinuxHowTos.org | Sockets Tutorial | N/A | 1 | 2013-09-20 | 1

## 9-30-13
Date: | 2013-09-30 |  |  | Total time:
Tasks | [5 empty] | Reading |  |  |  | Meetings
Task | Due date | Date Complete | % complete | Time spent (hours) | Notes | Author | Title | Chapter Titles | Time Spent | Date | Time
Android to Vex Comm | 2013-09-18 | 2013-09-20 | 100% | 2 | [5 empty] | 2013-09-24 | 1
Interrupt based obstacle avoidance | 2013-09-24 |  | 5% | 1 | [5 empty] | 2013-09-30
Project Report | 2013-09-26 | 2013-09-25 | 100% | 5.5
Project Plan 1 | 2013-10-01 |  | 90% | 3.5

## 10-7-13
Date: | 2013-10-07 |  |  | Total time:
Tasks | [5 empty] | Reading |  |  |  | Meetings
Task | Due date | Date Complete | % complete | Time spent (hours) | Notes | Author | Title | Chapter Titles | Time Spent | Date | Time
Read Android Documentation on UDP servers and using both send and receive in same app | 2013-10-03 | 2013-10-03 | 100% | 1
Code Android send/receive server | 2013-10-04 | 2013-10-04 | 100% | 2.5
Test Android send/receive server | 2013-10-07 | 2013-10-04 | 100% | 0.5
Code and test forwarding of movement commands, ignoring others for now | 2013-10-17 | 2013-10-04 | 100% | 0.5

## 10-21-13
Date: | 2013-10-21 |  |  | Total time: | 0.5
Tasks | [5 empty] | Reading |  |  |  | Meetings
Task | Due date | Date Complete | % complete | Time spent (hours) | Notes | Author | Title | Chapter Titles | Time Spent | Date | Time
[10 empty] | 2013-10-16 | 0.5

## 10-28-13
Date: | 2013-10-28 |  |  | Total time: | 10.5
Tasks | [5 empty] | Reading |  |  |  | Meetings
Task | Due date | Date Complete | % complete | Time spent (hours) | Notes | Author | Title | Chapter Titles | Time Spent | Date | Time
Merge GPS and Wifi Code | 2013-10-21 | 2013-10-22 | 100% | 3 | [5 empty] | 2013-10-23 | 0.5
Create Code for moving to GPS coordinate | 2013-10-26 |  | 90% | 5
Sending Waypoints from tablet to phone | 2013-10-26 | 2013-10-26 | 100% | 1.5
Robot Moves Straight | 2013-10-30 |  | 90% | 1

## 11-4-13
Date: | 2013-11-04 |  |  | Total time: | 10.5
Tasks | [5 empty] | Reading |  |  |  | Meetings
Task | Due date | Date Complete | % complete | Time spent (hours) | Notes | Author | Title | Chapter Titles | Time Spent | Date | Time
Getting Location Via Wifi | - | 2013-10-29 | 100% | 2 | [5 empty] | 2013-10-23 | 0
Sending location of phone back to tablet | - | 2013-10-29 | 100% | 0.5
Robot turns outside | 2013-10-30 | 2013-10-29 | 100% | 1
Robot Moves Straight | 2013-10-30 | 2013-10-30 | 100% | 0.5
Phase 3 Plan | 2013-11-05 |  | 90% | 2.5