## Tasks
Who | What | When | %Complete | Weight | Date Complete | Notes | Today: | 2013-10-04 | Requirement
All | Ensure all devices are secured in storage | ongoing | 0% |  |  |  | 0 |  | 0
Sei Jung | Android Tablet GUI | 2013-10-16 | 0% | 1 |  |  | 0 |  | 1
Sei Jung | Design new UI on paper to accommodate all new requirements in addition to existing movement GUI | 2013-10-04 | 0% | 0.2 |  |  | 0 |  | 1.1
Sei Jung | Create basic UI structure and intgrate with existing client from Android-Android communication | 2013-10-07 | 0% | 0.2 |  |  | 0 |  | 1.2
Sei Jung | Port existing movement GUI to new structure | 2013-10-11 | 0% | 0.25 |  |  | 0 |  | 1.3
Sei Jung | Learn format for GPS coordinates on Android to be used by GUI | 2013-10-14 | 0% | 0.1 |  |  | 0 |  | 1.4
Sei Jung | Create GPS (Waypoint entery and come home) part of GUI | 2013-10-16 | 0% | 0.25 |  |  | 0 |  | 1.5
Jacob | Communication between Vex, Phone, and Tablet | 2013-10-11 | 100% | 1 |  |  | 0 |  | 2
Jacob | Read information on using an Android device as both a send and receive server | 2013-10-03 | 100% | 0.1 | 2013-10-03 |  | 0 |  | 2.1
Jacob | Code send/receive server on single Android device | 2013-10-04 | 100% | 0.3 | 2013-10-04 |  | 0 |  | 2.2
Jacob | Test send/receive server as receiver from second Android device | 2013-10-07 | 100% | 0.15 | 2013-10-04 |  | 0 |  | 2.3
Jacob | Code printing and forwarding of movement commands, and printing of GPS commands, printing of errors for non-recognized commands | 2013-10-07 | 100% | 0.3 | 2013-10-04 |  | 0 |  | 2.4
Jacob | Test forwarding of movement commands from Tablet to the Vex | 2013-10-11 | 100% | 0.15 | 2013-10-04 |  | 0 |  | 2.5
Jerrell | Android able to get GPS coordinates | 2013-10-16 | 0% | 1 |  |  | 0 |  | 3
Jerrell | Read documentation on Android location API and location services API from Google Play SDK | 2013-10-03 | 0% | 0.1 |  |  | 1 |  | 3.1
Jerrell | Create collection of 5 known GPS locations on campus using Google Maps | 2013-10-04 | 0% | 0.05 |  |  | 0 |  | 3.2
Jerrell | Code basic app that gets the current GPS location when a button is pressed, displaying it to the screen and the time from when the button was pressed to when the GPS location is acquired | 2013-10-10 | 0% | 0.4 |  |  | 0 |  | 3.3
Jerrell | Test basic GPS locator app at known locations, comparing the results | 2013-10-11 | 0% | 0.1 |  |  | 0 |  | 3.4
Jerrell | Add functionality to GPS app that gets current facing direction | 2013-10-14 | 0% | 0.25 |  |  | 0 |  | 3.5
Jerrell | Test facing direction functionality | 2013-10-16 | 0% | 0.1 |  |  | 0 |  | 3.6
Jacob | Integrate GPS code with existing Phone send/receive server | 2013-10-21 | 0% | 1 |  |  | 0 |  | 3.7
Jerrell | Robot moves to a GPS Coordinate | 2013-10-26 | 0% | 1 |  |  | 0 |  | 4
Jerrell | Develop psuedocode algorithm for moving robot (with mounted phone) from current location to another location | 2013-10-21 | 0% | 0.4 |  |  | 0 |  | 4.1
Jerrell | Code algorithm in integrated send/receive GPS app | 2013-10-25 | 0% | 0.4 |  |  | 0 |  | 4.2
Jerrell | Test moving to a GPS Coordinate | 2013-10-26 | 0% | 0.2 |  |  | 0 |  | 4.3
Jacob | Robot moves in a straight line | 2013-10-25 | 0% | 1 |  |  | 0 |  | 5
Jacob | Modify robot frame to attempt to fix issue with robot veering left | 2013-10-22 | 0% | 0.3 |  |  | 0 |  | 5.1
Jacob | If necessary tune motors to get robot to move straight | 2013-10-24 | 0% | 0.2 |  |  | 0 |  | 5.2
Jacob | Test moving straight for 20m inside | 2013-10-25 | 0% | 0.3 |  |  | 0 |  | 5.3
Jacob | Test moving straight for 20m outside | 2013-10-25 | 0% | 0.2 |  |  | 0 |  | 5.4
Alex | Robot uses sensors (3 sensors) | 2013-10-26 | 0% | 1 |  |  | 0 |  | 6
Alex | Read API for Ultrasonic sensor (CSonar, CSonarController) | 2013-10-04 | 0% | 0.05 |  |  | 0 |  | 6.01
Alex | Implement group of sonar sensors (forward, backward, down facing both front and back) using interrupts | 2013-10-10 | 0% | 0.15 |  |  | 0 |  | 6.02
Alex | Test Sonar implmentation | 2013-10-11 | 0% | 0.15 |  |  | 0 |  | 6.03
Alex | Read examples on how to use the optical encoders | 2013-10-11 | 0% | 0.05 |  | https://code.google.com/p/terkos/source/browse/trunk/src/examples/linux/SonarRover/encoder.h?r=1216 | 0 |  | 6.04
Alex | Code reading data from the optical encoders | 2013-10-13 | 0% | 0.15 |  |  | 0 |  | 6.05
Alex | Test reading data from the optical encoders | 2013-10-14 | 0% | 0.1 |  |  | 0 |  | 6.06
Alex | Determine use for data from optical encoders caode and test using this data in some way related to this | 2013-10-16 | 0% | 0.1 |  |  | 0 |  | 6.07
Alex | Determine third sensor to use with the Vex and how this sensor can help us | 2013-10-21 | 0% | 0.05 |  |  | 0 |  | 6.08
Alex | Code reading data from this sensor and using it for something | 2013-10-25 | 0% | 0.1 |  |  | 0 |  | 6.09
Alex | Test reading data from the sensor and using it in some way | 2013-10-26 | 0% | 0.1 |  |  | 0 |  | 6.1
Alex | Cliff test | 2013-10-27 | 0% | 1 |  |  | 0 |  | 7
Alex (Sei Jung) | Determine highest possible drop that the Vex can navigate safely | 2013-10-24 | 0% | 0.2 |  |  | 0 |  | 7.1
Alex (Sei Jung) | Use Sonar implementation to use downward facing sensors to check if the robot is about to go over a drop greater than or equal to this distance | 2013-10-26 | 0% | 0.5 |  |  | 0 |  | 7.2
Alex (Sei Jung) | Test cliff sensors | 2013-10-27 | 0% | 0.3 |  |  | 0 |  | 7.3
Jacob | Merge Project code to final projects for submittal | 2013-10-30 | 0% |  |  |  | 0
Jerrell | Report | 2013-10-30 | 0% |  |  |  | 0
Sei Jung | Presentation | 2013-10-30 | 0% |  |  |  | 0

## RiskAnalysis
Requirement number | Points | Estimated Time (hours) | Risk Value | Task Value
(New Requirements)
1 | 0.2 | 10 | 1 | 0.02
2 | 0.2 | 12 | 0.9 | 0.015
3 | 0.15 | 7 | 0.5 | 0.010714
4 | 0.1 | 10 | 0.4 | 0.004
5 | 0.1 | 5 | 0.8 | 0.016
6 | 0.1 | 15 | 0.6 | 0.004
7 | 0.15 | 6 | 0.6 | 0.015