## Sheet1
Who | What | When | %Complete | Date Complete | Notes | Today: | 2013-09-07
Sei Jung | Place phone case on phone | 2013-09-04 | 100% | 2013-09-03 |  | 0
Sei Jung | Learn to set up/compile code for Vex | 2013-09-04 | 100% | 2013-09-03 |  | 0
Jerrell | Learn to operate/code in Debian Linux | 2013-09-04 | 100% | 2013-09-06 |  | 0
Alex | Learn to program ARM9 processor | 2013-09-04 | 0% |  |  | 1
Jacob | Set up development environment | 2013-09-04 | 100% | 2013-09-03 |  | 0
Sei Jung | Code Hello World Robot | 2013-09-05 | 100% | 2013-09-03 |  | 0
Jacob | Test Hello World Robot | 2013-09-05 | 100% | 2013-09-03 |  | 0
Jerrell | Learn Android programming basics | 2013-09-06 | 100% | 2013-09-05 |  | 0
Alex | Install ADT Eclipse plug-in | 2013-09-06 | 75% |  |  | 1
Sei Jung | Make sure tablet interfaces correctly with computer | 2013-09-06 | 0% |  |  | 1
Jacob | Code Hello World Tablet | 2013-09-06 | 0% |  |  | 1
Jerrell | Test Hello World Tablet | 2013-09-06 | 0% |  |  | 1
Sei Jung | Code Hello World Phone | 2013-09-06 | 100% | 2013-09-06 |  | 0
Alex | Test Hello World Phone | 2013-09-06 | 100% | 2013-09-06 |  | 0
Jerrell | Root Android Devices | 2013-09-08 | 0% |  |  | 0
Jacob | Ensure all devices are secured in storage | ongoing | 0% |  |  | 0
Jacob | Find motor spec sheets | 2013-09-08 | 100% | 2013-09-07 |  | 0
Jacob | Build Robot Frame | 2013-09-06 | 100% | 2013-09-03 |  | 0
Jacob | Code individual motor motion | 2013-09-08 | 100% | 2013-09-07 |  | 0
Jacob | Test individual motor motion | 2013-09-08 | 100% | 2013-09-07 |  | 0
Jacob | Create methods for moving robot forward/backward | 2013-09-08 | 100% | 2013-09-07 |  | 0
Jacob | Create methods for moving robot left/right | 2013-09-08 | 100% | 2013-09-07 |  | 0
Jacob | Test forward/backward motion | 2013-09-08 | 100% | 2013-09-07 | May need to do some mechanical fixes for making sure the wheels rotate smoothly | 0
Jacob | Test left/right motion | 2013-09-08 | 100% | 2013-09-07 |  | 0
Jacob | Determine sensors necessary to avoid obstacles | 2013-09-11 | 100% | 2013-09-07 | Use Bump Sensors | 0
Jacob | Find necessary references on sensors | 2013-09-11 | 0% |  |  | 0
Jacob | Code object avoidance | 2013-09-14 | 0% |  |  | 0
Jacob | Test obstacle avoidance | 2013-09-15 | 0% |  |  | 0
Alex | Choose communication medium between Phone/Tablet | 2013-09-06 | 0% |  |  | 1
Alex | Learn to use this medium for android | 2013-09-11 | 0% |  |  | 0
Alex | Write communication code | 2013-09-14 | 0% |  |  | 0
Alex | Send test traffic across communication channel | 2013-09-15 | 0% |  |  | 0
Sei Jung | Choose communication medium between Vex/Tablet | 2013-09-06 | 0% |  |  | 1
Sei Jung | Learn to send/receive this communication | 2013-09-11 | 0% |  |  | 0
Sei Jung | Write communication code | 2013-09-14 | 0% |  |  | 0
Sei Jung | Test communication code | 2013-09-15 | 0% |  |  | 0
Alex | Write GUI for controlling movement of the Vex | 2013-09-18 | 0% |  |  | 0
Alex | Test movement GUI | 2013-09-19 | 0% |  |  | 0
Sei Jung | Ensure efficient motor control algorithm | 2013-09-21 | 0% |  |  | 0
Sei Jung | Test robot moving forward/back/left/right on 10% grade | 2013-09-21 | 0% |  |  | 0
Jerrell | Read documentation on Vex controller communication | 2013-09-08 | 0% |  |  | 0
Jerrell | Create main application loop listening for input | 2013-09-14 | 0% |  |  | 0
Jerrell | Test reception of static speed parameter inputs | 2013-09-14 | 0% |  |  | 0
Jerrell | Calibrate speed based on joystick position | 2013-09-18 | 0% |  |  | 0
Jerrell | Modify control loop for dynamic speed | 2013-09-18 | 0% |  |  | 0
Jerrell | Test dynamic speeds | 2013-09-20 | 0% |  |  | 0
Alex | Modify control loop to allow turning while moving | 2013-09-22 | 0% |  |  | 0
Alex | Test complete movement | 2013-09-22 | 0% |  |  | 0
Jerrell | Determine high level emergency stop implementation | 2013-09-23 | 0% |  |  | 0
Jerrell | Write code to send/receive stop command | 2013-09-24 | 0% |  |  | 0
Jerrell | Test stop code | 2013-09-24 | 0% |  |  | 0