## 9-2-13
Date: | 2013-07-02 |  |  | Total time: | 6
Tasks | [5 empty] | Reading |  |  |  | Meetings
Task | Due date | Date Complete | % complete | Time spent (hours) | Notes | Author | Title | Chapter Titles | Time Spent | Date | Time
Set up GitHub | 2013-07-02 | 2013-08-30 | 100% | 2 | Handed off to Alex with assignment of responsibility | Github.com | Github Tutorial | Set up Git, Create a repository, Creating and deleting branches within your repository | 0.5 | 2013-08-30 | 1
Android Tutorial | 2013-07-02 |  | 0% | 0 | Ran out of time this weekend. Will complete in the next few days
Project Plan | 2013-07-02 | 2013-07-02 | 40% | 2.5 | Will be finished after the 8pm deadline

## 9-9-13
Date: | 2013-07-09 |  |  | Total time:
Tasks | [5 empty] | Reading |  |  |  | Meetings
Task | Due date | Date Complete | % complete | Time spent (hours) | Notes | Author | Title | Chapter Titles | Time Spent | Date | Time
Android Tutorial | 2013-09-04 |  | 5% | 0.25 |  | Github.com | Github Tutorial | Set up Git, Create a repository, Creating and deleting branches within your repository | 0.5 | 2013-07-06 | 0.5
Build Robot | 2013-09-06 | 2013-09-03 | 100% | 4
Set up Vex Dev Environment | 2013-09-04 | 2013-09-07 | 100% | 9
Find motor spec Sheets | 2013-09-08 | 2013-09-07 | 100% | 0.5 | Start 2:30
Code individual Motor motion | 2013-09-08 | 2013-09-07 | 100% | 0.25 | Start 3:00
Test individual Motor Motion | 2013-09-08 | 2013-09-07 | 100% | 0.25
Replace 3-wire motors with 2-wire | 2013-09-06 | 2013-09-07 | 100% | 0.75 | Start 3:30
Code Forward/Backward/Left/Right | 2013-09-08 | 2013-09-07 | 100% | 0.75
Test Forward/Backward/Left/Right | 2013-09-08 | 2013-09-07 | 100% | 0.25
Read documentation on Vex Controller Communication | 2013-09-08 |  | 5% | 0.5