## 7-2-13
Date: | 2013-07-02 |  |  | Total time: | 6
Tasks | [5 empty] | Reading |  |  |  | Meetings
Task | Due date | Date Complete | % complete | Time spent (hours) | Notes | Author | Title | Chapter Titles | Time Spent | Date | Time
Set up GitHub | 2013-07-02 | 2013-08-30 | 100% | 2 | Handed off to Alex with assignment of responsibility | Github.com | Github Tutorial | Set up Git, Create a repository, Creating and deleting branches within your repository | 0.5 | 2013-08-30 | 1
Android Tutorial | 2013-07-02 |  | 0% | 0 | Ran out of time this weekend. Will complete in the next few days
Project Plan | 2013-07-02 | 2013-07-02 | 40% | 2.5 | Will be finished after the 8pm deadline

## 7-9-13
Date: | 2013-07-09 |  |  | Total time:
Tasks | [5 empty] | Reading |  |  |  | Meetings
Task | Due date | Date Complete | % complete | Time spent (hours) | Notes | Author | Title | Chapter Titles | Time Spent | Date | Time
Android Tutorial | 2013-07-04 |  | 5% | 0.25 |  | Github.com | Github Tutorial | Set up Git, Create a repository, Creating and deleting branches within your repository | 0.5 | 2013-08-30 | 1